## Report
For current status, review the latest annual or quarterly fixed locations report. CAF II final milestone was December 31, 2020. FCC rules provided a cure period, until the end of 2021, for CAF II carriers to come into compliance with the final milestone. Regardless of status at the end of 2020, USAC and the FCC assessed compliance at the end of the 2021 for all CAF II carriers. The data is subject to compliance reviews per the FCC rules. The Compliance Gap % and Non-Compliance Tier shown takes into account the results of USAC's verification review process.
Program | Program Year | Milestone | Minimum Required Speed Tier for Milestone | SAC | Carrier | Holding Company | State | Total Obligation | Milestone Obligation | Total Certified Locations by End of Quarter | Compliance Gap % | Non-Compliance Tier | Notes
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 150072 | FRONTIER-AUSABLE VAL | FRONTIER COMMUNICATIONS CORPORATION | NY | 45610 | 45610 | 42553 | 6.702% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 200271 | CITIZENS-FRONTIER-WV | FRONTIER COMMUNICATIONS CORPORATION | WV | 89190 | 89190 | 80258 | 10.01% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 300615 | Frontier North, Inc. | FRONTIER COMMUNICATIONS CORPORATION | OH | 66592 | 66592 | 62793 | 5.705% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 310702 | CENTURYTEL MICHIGAN | CENTURYLINK, INC. | MI | 25230 | 25230 | 23893 | 5.299% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 320801 | CENTURYTEL OF ODON | CENTURYLINK, INC. | IN | 30052 | 30052 | 28430 | 5.397% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 330870 | RHINELNDER-FRONTIER | FRONTIER COMMUNICATIONS CORPORATION | WI | 76735 | 76735 | 70637 | 7.947% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 351127 | FRONTIER IOWA | FRONTIER COMMUNICATIONS CORPORATION | IA | 5438 | 5438 | 4822 | 11.33% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 355141 | QWEST CORP-IA | CENTURYLINK, INC. | IA | 34827 | 34827 | 31111 | 10.67% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 361123 | CITIZENS-FRONTIER-MN | FRONTIER COMMUNICATIONS CORPORATION | MN | 46910 | 46910 | 42904 | 8.54% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 365142 | QWEST CORP-MN | CENTURYLINK, INC. | MN | 114739 | 114739 | 105176 | 8.335% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 371128 | CITIZENS-FRONTIER-NE | FRONTIER COMMUNICATIONS CORPORATION | NE | 3380 | 3380 | 3109 | 8.018% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 385144 | QWEST CORP-ND | CENTURYLINK, INC. | ND | 8044 | 8044 | 7615 | 5.333% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 395145 | QWEST CORP-SD | CENTURYLINK, INC. | SD | 15071 | 15071 | 13127 | 12.9% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 421151 | SPECTRA COMMUNICATIONS GROUP, LLC DBA CENTURYLINK | CENTURYLINK, INC. | MO | 152652 | 152652 | 143695 | 5.868% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 452172 | CITZENS-FRNTR-RURAL | FRONTIER COMMUNICATIONS CORPORATION | AZ | 22768 | 22768 | 15477 | 32.02% | 3
Revised A-CAM I | 2020 | 40% | 10 Mbps/1 Mbps | 462193 | NUCLA-NATURITA TEL | Nucla-Naturita Telephone Company | CO | 340 | 136 | 22 | 83.82% | 4
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 465102 | QWEST CORP-CO | CENTURYLINK, INC. | CO | 53139 | 53139 | 50161 | 5.604% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 472225 | CENTURYTEL OF IDAHO | CENTURYLINK, INC. | ID | 12367 | 12367 | 10643 | 13.94% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 494449 | NAVAJO-NM-FRONTIER | FRONTIER COMMUNICATIONS CORPORATION | NM | 7032 | 7032 | 5050 | 28.19% | 3
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 504429 | CITIZENS-FRONTIER-UT | FRONTIER COMMUNICATIONS CORPORATION | UT | 5140 | 5140 | 3765 | 26.75% | 3
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 525161 | QWEST CORP-WA | CENTURYLINK, INC. | WA | 58961 | 58961 | 55824 | 5.32% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 535163 | QWEST CORP-OR | CENTURYLINK, INC. | OR | 41785 | 41785 | 37360 | 10.59% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 541863 | Frontier Communications of the Southwest | FRONTIER COMMUNICATIONS CORPORATION | CA | 90224 | 90224 | 81916 | 9.208% | 1
Revised A-CAM I | 2020 | 40% | 10 Mbps/1 Mbps | 542321 | HAPPY VALLEY TEL CO | Telephone and Data Systems, Inc. | CA | 2339 | 935 | 443 | 52.62% | --- | Note 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 552302 | Frontier Communications of the Southwest, Inc. | FRONTIER COMMUNICATIONS CORPORATION | NV | 2970 | 2970 | 2761 | 7.037% | 1
CAF II | 2020 | 100% | 10 Mbps/1 Mbps | 401705 | CENTURYTEL- ARKANSAS | CENTURYLINK, INC. | AR | 45708 | 45708 | 44262 | 3.164% | --- | Note 2

## Notes
Notes
1. In September 2020, TDS requested a waiver of it's California service milestone because TDS was unable to complete its planned buildout in Winterhaven and Hornitas areas due to COVID-19 pandemic restrictions. This petition for waiver was granted on June 1, 2021 (DA-21-643).
2. Non-compliant after March 1, 2021 filing deadline. Back in compliance Q2. Non-compliant as a result of verification for Q4.