## Report
Note 1. Selected review for progress towards 40% milestone
Note 2. Carriers with a compliance gap percent greater than 0% but less than 5% do not fall into a non-compliance tier
Program | Milestone Type | Milestone % | Minimum Required Speed Tier for Milestone | SAC | Carrier | Holding Company | State | Total Obligation | Milestone Obligation | Certified Locations Deployed by End of Program Year | Total Locations Counted Toward Milestone | Compliance Gap % | In Compliance | Non-Compliance Tier | Notes
A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 351108 | BARNES CITY COOP | Barnes City Cooperative Telephone Company | IA | 97 | 48 | 137 | 128 | 0% | Yes | N/A
A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 341075 | REYNOLDS TEL CO, INC | Reynolds Telephone Company | IL | 154 | 77 | 186 | 183 | 0% | Yes | N/A
A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 351310 | TITONKA TEL CO | Titonka Telephone Company | IA | 279 | 139 | 322 | 322 | 0% | Yes | N/A
A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 330905 | MANAWA TEL CO | Wood County Telephone Company | WI | 1645 | 822 | 1403 | 1313 | 0% | Yes | N/A
A-CAM I Count |  |  |  | 4
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 462181 | BIJOU TEL COOP ASSOC | Bijou Telephone Cooperative Association Inc. | CO | 801 | 400 | 775 | 758 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 473333 | Fremont Telecom - RoR | Blackfoot Telephone Cooperative, Inc. | ID | 1891 | 945 | 2133 | 1957 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 330865 | CLEAR LAKE TEL CO-WI | Clear Lake Telephone Company | WI | 1101 | 550 | 914 | 899 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 290562 | DEKALB TEL COOP | DeKalb Telephone Cooperative, Inc. | TN | 7814 | 3907 | 8001 | 7695 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 150093 | EMPIRE TEL CORP | Empire Telephone Corp/North Penn Telephone Co. | NY | 2067 | 1033 | 1969 | 1901 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 442070 | ETEX TEL COOP INC | Etex Telephone Cooperative, Inc. | TX | 5602 | 2801 | 3417 | 3278 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 190226 | Lumos Telephone Inc | Lumos Networks Corp. | VA | 3638 | 1819 | 1995 | 1946 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 613028 | SUMMIT TEL & TEL -AK | Remote Control, Inc. | AK | 74 | 37 | 121 | 81 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 532375 | ROOME TELECOMM INC | Roome Telecommunications Inc. | OR | 353 | 176 | 309 | 260 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 280454 | FRANKLIN TEL CO - MS | Telapex, Inc. | MS | 8559 | 4279 | 8967 | 8198 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 240551 | WILLISTON TEL CO | Telephone and Data Systems, Inc. | SC | 3723 | 1861 | 2330 | 2034 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 120045 | KEARSARGE TEL CO | Telephone and Data Systems, Inc. | NH | 1877 | 938 | 1033 | 1029 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 542321 | HAPPY VALLEY TEL CO | Telephone and Data Systems, Inc. | CA | 2339 | 1169 | 962 | 883 | 24.49% | No | 2
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 300654 | RIDGEVILLE TEL CO | The Ridgeville Telephone Company | OH | 393 | 196 | 392 | 389 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 502287 | UBTA-UBET Communications, Inc | UBTA-UBET Communications | UT | 6289 | 3144 | 5246 | 5073 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 371537 | DALTON TEL CO, INC | USConnect Holdings, Inc. | NE | 94 | 47 | 203 | 198 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 432032 | VALLIANT TEL CO | Valliant Telephone Company, Inc. | OK | 1615 | 807 | 1014 | 774 | 4.04% | No | N/A | Note 2
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 240550 | WEST CAROLINA RURAL | West Carolina Rural Telephone Cooperative, Inc. | SC | 1263 | 631 | 1244 | 1165 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 361505 | WIKSTROM TEL CO, INC | Wikstrom Telephone Company, Inc. | MN | 4151 | 2075 | 3894 | 3887 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 351342 | WOOLSTOCK MUTUAL | Woolstock Mutual Telephone Association | IA | 61 | 30 | 146 | 128 | 0% | Yes | N/A
Revised A-CAM I | Interim | 50% | 10 Mbps/1 Mbps | 401712 | MOUNTAIN VIEW TEL CO | Yelcot Holding Group, Inc. | AR | 5801 | 2900 | 4877 | 4875 | 0% | Yes | N/A
Revised A-CAM I Count |  |  |  | 21
AK Plan Wireline | Interim | 5-Year | 1000 Mbps/100 Mbps | 613006 | COPPER VALLEY TEL | COPPER VALLEY TEL | AK | 3515 | 2828 | 2828 | 2828 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613006 | COPPER VALLEY TEL | COPPER VALLEY TEL | AK | 138 | 138 | 282 | 150 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 50 Mbps/5 Mbps | 613006 | COPPER VALLEY TEL | COPPER VALLEY TEL | AK | 278 | 278 | 278 | 278 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 100 Mbps/5 Mbps | 613007 | CORDOVA TEL COOP | CORDOVA TEL COOP | AK | 850 | 425 | 425 | 425 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613007 | CORDOVA TEL COOP | CORDOVA TEL COOP | AK | 0 | 17 | 40 | 36 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 10 Mbps/1 Mbps | 613011 | INTERIOR TEL CO INC | AMERICAN BROADBAND COMMUNICATIONS ET AL. | AK | 124 | 124 | 132 | 130 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 100 Mbps/5 Mbps | 613013 | KETCHIKAN PUBLIC UT | CITY OF KETCHIKAN | AK | 2439 | 1722 | 1722 | 1722 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613013 | KETCHIKAN PUBLIC UT | CITY OF KETCHIKAN | AK | 287 | 430 | 1254 | 1017 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 50 Mbps/5 Mbps | 613013 | KETCHIKAN PUBLIC UT | CITY OF KETCHIKAN | AK | 107 | 107 | 107 | 107 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613011 | MUKLUK TEL CO INC | AMERICAN BROADBAND COMMUNICATIONS ET AL. | AK | 1771 | 1753 | 1753 | 1753 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 6 Mbps/1 Mbps | 613018 | NUSHAGAK ELEC & TEL | NUSHAGAK ELEC & TEL | AK | 146 | 146 | 319 | 315 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613019 | OTZ TEL COOPERATIVE | OTZ TELEPHONE COOPERATIVE, INC. | AK | 1249 | 694 | 1210 | 1192 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 1 Mbps/256 Kbps | 613023 | UNITED-KUC, INC., AN AFFILIATE OF UNITED COMPANIES | GCI HOLDINGS, INC. | AK | 1063 | 1063 | 6051 | 5738 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 10 Mbps/1 Mbps | 613023 | UNITED-KUC, INC., AN AFFILIATE OF UNITED COMPANIES | GCI HOLDINGS, INC. | AK | 8621 | 4311 | 4311 | 4311 | 0% | Yes | N/A
AK Plan Wireline | Interim | 5-Year | 25 Mbps/3 Mbps | 613023 | UNITED-KUC, INC., AN AFFILIATE OF UNITED COMPANIES | GCI HOLDINGS, INC. | AK | 324 | 324 | 324 | 324 | 0% | Yes | N/A
AK Plan Wireline Count |  |  |  | 15
CAF II ACS | Interim | 60% | 10 Mbps/1 Mbps | 613000 | ACS OF ANCHORAGE | ALASKA COMMUNICATIONS SYSTEMS HOLDINGS, INC. | AK | 31571 | 18943 | 18717 | 18716 | 1.2% | No | N/A | Note 2
CAF II ACS Count |  |  |  | 1
CAF II Auction | N/A | N/A | 25 Mbps/3 Mbps | 359146 | AMG TECHNOLOGY INVESTMENT GROUP, LLC D/B/A NEXTLINK INTERNET | AMG Technology Investment Group | IA | 15097 | 6039 | 1256 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 25 Mbps/3 Mbps | 519019 | TRI COUNTY TELEPHONE ASSOCIATION, INC. | BHT Holdings | WY | 1930 | 772 | 1520 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 25 Mbps/3 Mbps | 159041 | Hughes Network Systems, LLC | Hughes Network Systems, LLC | NY | 22305 | 8922 | 5824 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 100 Mbps/20 Mbps | 399005 | MIDCONTINENT COMMUNICATIONS | Midcontinent Communications | SD | 892 | 356 | 201 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 100 Mbps/20 Mbps | 389011 | MIDCONTINENT COMMUNICATIONS | Midcontinent Communications | ND | 1069 | 427 | 521 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 100 Mbps/20 Mbps | 369015 | MIDCONTINENT COMMUNICATIONS | Midcontinent Communications | MN | 7410 | 2964 | 42 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | N/A | N/A | 25 Mbps/3 Mbps | 469036 | VIASAT | Viasat Communications, Inc. | CO | 6517 | 2606 | 1952 | N/A | N/A | N/A | N/A | Note 1
CAF II Auction | LOC Reduction | 20% | 25 Mbps/3 Mbps | 529026 | COMPUTER 5 INC. D/B/A LOCALTEL COMMUNICATIONS | Computer 5 Inc. d/b/a LocalTel Communications | WA | 1910 | 382 | 394 | 388 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 100 Mbps/20 Mbps | 429043 | AIR LINK RURAL BROADBAND, LLC | Airlink Rural broadband LLC | MO | 2321 | 464 | 551 | 546 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 1 Gbps/500 Mbps | 279054 | ALLEN'S T.V. CABLE SERVICE, INC. | Allen's T.V. Cable Service, Inc. | LA | 794 | 159 | 212 | 211 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 25 Mbps/3 Mbps | 409046 | ARISTOTLE UNIFIED COMMUNICATIONS | Aristotle Unified Communications | LA | 3191 | 638 | 1179 | 950 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 80% | 1 Gbps/500 Mbps | 429037 | CALLABYTE TECHNOLOGY, LLC | Callabyte Technology, LLC | MO | 1425 | 1188 | 1418 | 1368 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 100% | 1,000 Mbps/500 Mbps | 305062 | CINCINNATI BELL-OH | CINCINNATI BELL INC. | OH | 20 | 20 | 21 | 21 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 80% | 1 Gbps/500 Mbps | 429038 | CO-MO COMM, INC. | Co-Mo Communications, Inc. | MD | 8356 | 6685 | 7299 | 6896 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 80% | 100 Mbps/20 Mbps | 159034 | Gtel Teleconnections | Gtel Teleconnections | NY | 260 | 208 | 264 | 254 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 1 Gbps/500 Mbps | 623100 | HAWAIIAN TELCOM, INC | Hawaiian Telcom, Inc. | HI | 3936 | 787 | 979 | 927 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 40% | 100 Mbps/20 Mbps | 439078 | PLAINS INTERNET, LLC | Plains Internet, LLC | OK | 3194 | 1278 | 1405 | 1289 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 60% | 25 Mbps/3 Mbps | 479027 | RED SPECTRUM | Red Spectrum Communications, LLC | ID | 185 | 111 | 159 | 140 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 40% | 1000 Mbps/500 Mbps | 199025 | SUNSET DIGITAL COMMUNICATIONS, LLC | Sunset Digital Communications, LLC | VA | 6998 | 2800 | 2869 | 2859 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 25 Mbps/3 Mbps | 349043 | W.A.T.C.H. TV COMPANY | W.A.T.C.H. TV Company | IL | 6041 | 1208 | 2052 | 2052 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 100 Mbps/20 Mbps | 419047 | WISPER ISP, LLC | Wisper ISP, LLC | KS | 414 | 83 | 189 | 183 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 100 Mbps/20 Mbps | 349045 | WISPER ISP, LLC | Wisper ISP, LLC | IL | 8907 | 1781 | 2363 | 2362 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 100 Mbps/20 Mbps | 409047 | WISPER ISP, LLC | Wisper ISP, LLC | AR | 102 | 20 | 58 | 49 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 100 Mbps/20 Mbps | 439082 | WISPER ISP, LLC | Wisper ISP, LLC | OK | 2443 | 489 | 878 | 852 | 0% | Yes | N/A
CAF II Auction | LOC Reduction | 20% | 25/3 Mbps, 100/20 Mbps | 429045 | WISPER ISP, LLC | Wisper ISP, LLC | MO | 67628 | 13654 | 17456 | 17455 | 0% | Yes | N/A
CAF II Auction Count |  |  |  | 25
RBE | 100% | 100% | 100 Mbps/25 Mbps | 536129 | DOUGLAS SERVICES, INC. | Douglas Services, Inc. | OR | 2495 | 2495 | 2500 | 2183 | 12.52% | No | 1
RBE | 100% | 100% | 100 Mbps/25 Mbps | 436144 | NORTHEAST RURAL SERVICES. | Northeast Rural Services, Inc. | OK | 25 | 25 | 32 | 24 | 4% | No | N/A | Note 2
RBE | 100% | 100% | 100 Mbps/25 Mbps | 436148 | NORTHEAST RURAL SERVICES. | Northeast Rural Services, Inc. | OK | 20 | 20 | 24 | 20 | 0% | Yes | N/A
RBE | 100% | 100% | 10 Mbps/1 Mbps | 346326 | DELTA COMMUNICATIONS LLC | Delta Communications, L.L.C. d/b/a Clearwave | IL | 108 | 108 | 109 | 97 | 10.19% | No | 1
RBE Count |  |  |  | 4
RDOF | LOC Reduction | 100% | 1 Gbps/500 Mbps | 431995 | HINTON TEL CO | Hinton Telephone Company | OK | 120 | 120 | 121 | 120 | 0% | Yes | N/A
RDOF | LOC Reduction | 20% | 1 Gbps/500 Mbps | 299013 | AENEAS COMMUNICATIONS, LLC | Aeneas Communications, LLC | TN | 10393 | 2079 | 3269 | 3239 | 0% | Yes | N/A
RDOF | LOC Reduction | 40% | 1 Gbps/500 Mbps | 159049 | POINT BROADBAND FIBER HOLDING, LLC | Point Broadband Fiber Holdings LLC | NY | 2568 | 1028 | 2035 | 1987 | 0% | Yes | N/A
RDOF | LOC Reduction | 60% | 1 Gbps/500 Mbps | 299035 | TEPA CONNECT, LLC | Tippah Electric Power Association | TN | 104 | 63 | 65 | 64 | 0% | Yes | N/A
RDOF | LOC Reduction | 40% | 1 Gbps/500 Mbps | 289043 | TEPA CONNECT, LLC | Tippah Electric Power Association | MS | 2163 | 866 | 1156 | 1114 | 0% | Yes | N/A
RDOF | LOC Reduction | 60% | 1 Gbps/500 Mbps | 419050 | WTC COMMUNICATIONS, INC. | WTC Communications, Inc. | KS | 174 | 105 | 110 | 110 | 0% | Yes | N/A
RDOF Count |  |  |  | 6
Grand Count |  |  |  | 76